## Sheet1
No. | Item | Dependencies | Business Value | Release Schedule
1 | Implement a mySQL database |  | 8 | Sprint #1
2 | Design UI |  | 6 | Sprint #1
3 | Add sales records to database | 1 | 10 | Sprint #1
4 | Edit sale records | 3 | 10 | Sprint #1
5 | Display sale records | 3 | 10 | Sprint #1
6 | Display monthly sales report | 3 | 10 | Sprint #1
7 | Generate a monthly sales report as CSV | 3 | 10 | Sprint #2
8 | Add item Information (inventory) | 1 | 6 | Sprint #1
9 | Edit item information | 8 | 6 | Sprint #1
10 | Display Item Information | 9 | 6 | Sprint #2
11 | Predict sales of an item monthly | 8 | 10 | Sprint #2
12 | Predict sales of a group of items monthly | 8 | 10 | Sprint #2
13 | Alerts for low stock | 8 | 8 | Sprint #2
14 | Implement sales reducing stock automatically | 8 | 5 | Sprint #2
15 | Create UI | All above | 8 | Sprint #2
16 | Login system | 15 | 4 | Sprint #2
17 | Online data sync | 14 | 5 | Sprint #2
18 | Software information/Hand over | All above | 7 | Sprint #2