## Sheet1
No. | Item | Dependencies | Business Value | Release Schedule
1 | Implement a mySQL database |  |  | Sprint #1
2 | Design UI |  |  | Sprint #1
3 | Add sales records to database | 1 |  | Sprint #1
4 | Edit sale records | 3 |  | Sprint #1
5 | Display sale records | 3 |  | Sprint #1
6 | Display monthly sales report | 3 |  | Sprint #1
7 | Generate a monthly sales report as CSV | 3 |  | Sprint #2
8 | Add item Information (inventory) | 1 |  | Sprint #1
9 | Edit item information | 8 |  | Sprint #1
10 | Display Item Information | 9
11 | Predict sales of an item monthly | 8 |  | Sprint #2
12 | Predict sales of a group of items monthly | 8 |  | Sprint #2
13 | Alerts for low stock | 8 |  | Sprint #2
14 | Implement sales reducing stock automatically | 8 |  | Sprint #2
15 | Create UI | All above |  | Sprint #2
16 | Login system | 15 |  | Sprint #2
17 | Online data sync | 14 |  | Sprint #2
18 | Software information/Hand over | All above |  | Sprint #2